A Standardized Benchmarking Protocol

for Comparing Agentic AI Systems with Rule-Based and

Single-Model AI Baselines Using Clinically Relevant Metrics

Jeevan Reddy Miriyala · Devaguru Nanduri · Farhan Khan · Samhita Reddy Mentor: Dr. Resham Raj

# 1.  Project Overview

Artificial Intelligence has become integral to modern healthcare, supporting clinical decision-making, diagnosis assistance, and patient risk assessment. This research develops a standardized, reproducible benchmarking protocol to objectively compare three classes of AI systems: rule-based expert systems, single-model AI baselines, and agentic AI systems with planning and reasoning capabilities.

|  | Research Gap Existing evaluation methods rely heavily on generic ML metrics (accuracy, F1) that fail to capture real-world clinical requirements. No unified benchmarking protocol currently exists for comparing agentic AI with conventional AI using clinically meaningful metrics. This project fills that gap with a reusable, fair, and reproducible framework. |
| --- | --- |

# 2.  Objectives

- Develop a standardized and reproducible benchmarking protocol for clinical AI systems

- Compare agentic AI systems with rule-based and single-model AI baselines under controlled conditions

- Incorporate clinically relevant evaluation metrics beyond traditional performance scores

- Analyze the strengths, limitations, and trade-offs of agentic AI in clinical decision-making

# 3.  Clinical Task & Dataset Selection

The benchmark will focus on:

| Clinical Task | Diabetes Risk Prediction / Patient Readmission Risk |
| --- | --- |
| Dataset | PIMA Indians Diabetes Dataset (freely available on Kaggle — no institutional access required) |
| Why this task? | Tabular, clean, well-understood. Rich literature. Rule-based systems easy to define. LLMs reason naturally over patient features. |
| Agentic Approach | ReAct-style LLM with tool-use prompting via Claude or GPT-4 free API tier |

# 4.  3-Week Execution Plan

WEEK 1 — Setup & Baselines • Days 1–7

Days 1–2: Dataset & Environment Setup

- Download PIMA Diabetes Dataset from Kaggle (free, no signup needed)

- Set up Python environment: scikit-learn, pandas, numpy, matplotlib

- Obtain free API access: Claude API or OpenAI free credits

Days 3–4: Rule-Based Expert System

- Define clinical threshold rules (e.g. Glucose > 140 → high risk; BMI > 30 + Age > 45 → elevated risk)

- Combine rules into a scoring system — this is your 'expert system' baseline

Days 5–6: Single-Model AI Baseline

- Train Logistic Regression (simple, interpretable) and Random Forest (stronger, explainable)

- Record: accuracy, precision, recall, F1, AUC-ROC, sensitivity, specificity

Day 7: Calibration & Consistency Testing for Baselines

- Plot reliability/calibration curves for both models

- Run predictions 3× on identical inputs to verify deterministic consistency (should be 100%)

WEEK 2 — Agentic AI System • Days 8–14

Days 8–9: Design the ReAct Agent

Structure the LLM agent as a 4-step reasoning loop:

- Step 1 — Observe: Receive patient features as structured text

- Step 2 — Think: LLM reasons about individual risk factors

- Step 3 — Act: LLM calls a lookup tool (BMI table, glucose thresholds)

- Step 4 — Output: Final risk decision + natural language explanation

Days 10–11: Implement & Run the Agent

- Convert 50–100 PIMA rows into natural language patient descriptions

- Run each through the LLM agent via API

- Log: decision, reasoning chain, time-to-decision, token cost

Days 12–13: Evaluate Agent on Clinical Metrics

Compute all metrics across all three systems side by side (see Evaluation Metrics section).

Day 14: Error Severity Analysis

- Classify each model's errors as 'clinically minor' vs 'clinically serious'

- For diabetes: a false negative (missed diabetic) is more dangerous than a false positive — quantify this distinction

- This is one of the project's key novel contributions

WEEK 3 — Paper Writing & Submission • Days 15–21

Days 15–16: Results & Figures

- Generate comparison tables and bar charts across all three systems

- Calibration plots, ROC curves, and decision-consistency heatmaps

Days 17–18: Write the Paper

Target structure (6–8 pages): Abstract · Introduction · Related Work · Methodology · Experimental Setup · Results & Analysis · Discussion · Conclusion

Day 19: Internal Review

- Each team member reviews one section

- Mentor feedback round with Dr. Resham Raj

Days 20–21: Polish & Submit

- Format to target venue style guidelines

- Final proofread, finalize all figures and tables

# 5.  Evaluation Metrics

All three systems will be evaluated on identical datasets and conditions. The table below summarizes the full set of clinically relevant metrics:

| Metric | Rule-Based | Single-Model AI | Agentic LLM |
| --- | --- | --- | --- |
| Accuracy | ✓ | ✓ | ✓ |
| Sensitivity / Specificity | ✓ | ✓ | ✓ |
| Calibration | ✓ | ✓ | ✓ |
| Decision Consistency | ✓ | ✓ | ✓ (run 3×) |
| Time-to-Decision | ✓ | ✓ | ✓ |
| Interpretability | Manual rules | SHAP values | Chain-of-thought |
| Error Severity | FP/FN classify | FP/FN classify | FP/FN classify |

|  | Key Clinical Insight Standard ML metrics such as accuracy are insufficient for clinical AI evaluation. Error Severity: In diabetes prediction, a false negative (missed case) is clinically more dangerous than a false positive. Decision Consistency: Agentic/LLM systems are inherently stochastic — this must be explicitly measured (run identical inputs 3×). Interpretability: Rule-based → explicit rules; ML → SHAP values; Agentic → chain-of-thought reasoning. |
| --- | --- |

# 6.  Team & Division of Work

| Team Member | Primary Role | Key Responsibilities |
| --- | --- | --- |
| Jeevan Reddy Miriyala | Agentic LLM System Implementation | LLM agent design, ReAct prompting loop, API integration |
| Devaguru Nanduri | Rule-Based & ML Baselines | Expert system rules, Logistic Regression, Random Forest training |
| Farhan Khan | Metrics & Evaluation Pipeline | Metric computation, calibration curves, ROC plots, charts |
| Samhita Reddy | Research Writing & Literature | Paper drafting, related work, discussion, formatting |

# 7.  Key Novelty & Significance

|  | Research Contribution The novelty of this project is NOT in building a new AI model — it is in the benchmarking protocol itself. The framework provides a reusable, fair evaluation methodology that other researchers can apply to any clinical task. This is a legitimate and publishable research contribution even with freely available tools and datasets. |
| --- | --- |

The expected outcomes of this project include:

- A reusable benchmarking protocol enabling fair comparison between agentic and traditional AI systems in healthcare

- Insights into the practical advantages and limitations of agentic AI for clinical decision support

- Actionable guidance for researchers, clinicians, and policymakers evaluating safe AI adoption in clinical settings

- A fully documented, reproducible experimental setup with open-access datasets and publicly available tools